## Project Plan
Product Injury Data Analysis |  | Project plan based on CRISP-DM Methodology, as described by Northeastern University
https://graduate.northeastern.edu/resources/data-analysis-project-lifecycle/
Action | Start Date | Target Date | Date Completed | % Complete | Notes
Understand Business
Define objectives |  | n/a | 2024-02-01 | 100% | Captured in presentation slides
Define scope of work |  | n/a | 2024-02-01 | 100% | Captured in presentation slides
Define deliverables |  | n/a | 2024-02-01 | 100% | Captured in project plan
Gather background information |  | n/a | 2024-02-01 | 100% | Captured in presentation slides (appendix)
Deliverable: Project overview documentation |  | n/a | 2024-02-01 | 100% | Captured in presentation slides
Understand Data
Codes / Lookup Table |  |  | 2024-02-05 | 100% | Jupyter notebook - DataPrepCodes
Collect data |  |  | 2024-02-01 | 100%
Load data |  |  | 2024-02-01 | 100%
Preview data |  |  | 2024-02-01 | 100%
Delete NaN rows and columns |  |  | 2024-02-01 | 100%
Identify and describe variables |  |  | 2024-02-01 | 100%
Remove irrelevant variables |  |  | 2024-02-01 | 100%
Rename variables for clarity |  |  | 2024-02-01 | 100%
Update datatypes and formats as needed |  |  | 2024-02-05 | 100%
Injury data
Collect data
Load data
Preview data
Indentify and describe variables
Remove irrelevant variables
Rename variables for clarity
Update datatypes and formats as needed
Deliverable: Document data source(s) |  |  | 2024-02-01 | 100% | Captured in presentation slides
Deliverable: Source control project setup
Deliverable: Published dataset ready for prep/cleaning
Deliverable: Documentation of work completed and findings
Data Preparation
Codes / Lookup Table |  |  | 2024-02-05 | 100% | Jupyter notebook - DataPrepCodes
Remove duplicate data |  |  | 2024-02-05 | 100%
Handle missing data |  |  | 2024-02-05 | 100%
Verify data integrity and check for outliers |  |  | 2024-02-05 | 100%
Save to Excel |  |  | 2024-02-05 | 100%
Injury Data
Remove duplicate data
Handle missing data
Look for and cleanup miscoded data
Verify data integrity and check for outliers
Deliverable: Published dataset ready for EDA
Deliverable: Documentation of work completed and findings
Exploratory Data Analysis
Exploratory Data Analysis
Data Visualizations
Deliverable: Checklist of questions to be explored
Deliverable: Documentation of work completed and findings
Validation and QA
Review findings
Validate process
Validate data
Deliverable: Documentation of work completed and findings
Deliverable: Review objectives - is more work needed?
Visualization and Presentation
Review all past deliverables for clarity and consistency
Craft a compling story
Document recommendations
Deliverable: Final visualizations
Deliverable: Final presentation
Project Closeout
Check-in all final code and documentations
Publish project assets and findings as appropriate
Data Collection
NEIS data downloads | 2024-01-19 | 2024-01-19 | 2024-01-19 | 100% | Excel files from 2013 - 2022
Load injury data to Azure SQL | 2024-01-19 | 2024-01-19 | 2024-01-19 | 100% | Database name = ProductInjury
Data Preparation
Validate (and correct) consistency of variables names | 2024-01-19 | 2024-01-19 | 2024-01-19 | 100% | Validated Manually in MSSM
Validate (and correct) consistency of codes / labels | 2024-01-19 | 2024-01-19 | 2024-01-24 | 100% | Python Notebook - DataPrepCodes
Load scrubbed codes and labels to Azure SQL | 2024-01-19 | 2024-01-19 | 2024-01-28 | 100% | Imported using MSSM
Validate and merge injury datasets | 2024-01-28 | 2024-01-28 |  | 50% | Python Notebook - DataPrepInjuries
Load injury data to Azure SQL |  |  |  |  | Python Notebook - DataPrepInjuries
Data Analysis
Number of products tracked
Distribution of injuries by product
Findings / Presentation
Review DataPrepCodes notebook
Project Close Out

## Analysis Checklist
Metric / Report / Graph | Status
# of Product Tracked

## Issue Log
Issue | Issue Type | Date Entered | Date Resolved | Status | Resolution
Cannot read neiss2020, neis2021, or neis2022 Excel files. The folowing error is produced: Unable to read workbook: could not read properties from <filename>. | File Format | 2024-01-18 | 2024-01-19 | Closed | Resolved this issue for each file by copying the data to a new Excel file.
Warninng reading Data Dictionary | File Format | 2024-02-02 | 2024-02-02 | Closed | Cleared print area in Excel and saved file

## Data Cleanup Log
Issue | Issue Type | Date Entered | Status | Resolution
Variable name mismatch - before 2020 Narrative was used, from 2020 on, Narrative_1 is used | Variable Name Consistency | 2024-01-11 | Closed | Updated column names in MSSM using the Design feature
Non-numeric data in Strating and Ending values in code / label data | Data Type Issue | 2024-01-15 | Closed | Stripped spaces and deleted rows with a '.' as a starting or ending value in Python
Product codes with missing labels | Data Issue | 2024-01-19 | Closed | Deleted rows in Python
Age > 200 is under 2 years and translates to age in months using the codes table |  | 2024-01-16 | Open
Age 0 = unknown, not less than 1, 16 occurances of unknown age |  | 2024-01-16 | Open
Codes table contains null rows |  | 2024-01-16 | Open
Labels for Fire codes are unclear and should be updated per page 43 of the manual |  | 2024-01-17 | Open