## Project Plan
Product Injury Data Analysis |  | Project plan based on CRISP-DM Methodology, as described by Northeastern University
https://graduate.northeastern.edu/resources/data-analysis-project-lifecycle/
Action | Start Date | Target Date | Date Completed | % Complete | Notes
Understand Business
Define objectives |  | n/a | 2024-02-01 | 100% | Captured in presentation slides
Define scope of work |  | n/a | 2024-02-01 | 100% | Captured in presentation slides
Define deliverables |  | n/a | 2024-02-01 | 100% | Captured in project plan
Gather background information |  | n/a | 2024-02-01 | 100% | Captured in presentation slides (appendix)
Deliverable: Project overview documentation |  | n/a | 2024-02-01 | 100% | Captured in presentation slides
Understand Data
Review injury data methodology
Codes / Lookup Table |  |  | 2024-02-05 | 100% | Jupyter notebook - DataPrepCodes
Collect data |  |  | 2024-02-01 | 100%
Load data |  |  | 2024-02-01 | 100%
Preview data |  |  | 2024-02-01 | 100%
Delete NaN rows and columns |  |  | 2024-02-01 | 100%
Identify and describe variables |  |  | 2024-02-01 | 100%
Remove irrelevant variables |  |  | 2024-02-01 | 100%
Rename variables for clarity |  |  | 2024-02-01 | 100%
Update datatypes and formats as needed |  |  | 2024-02-05 | 100%
Injury data
Collect data |  |  | 2024-02-06 | 100%
Load data |  |  | 2024-02-06 | 100%
Preview data |  |  | 2024-02-06 | 100%
Indentify and describe variables |  |  | 2024-02-06 | 100%
Remove irrelevant variables |  |  | 2024-02-06 | 100%
Rename variables for clarity |  |  | 2024-02-06 | 100%
Update datatypes and formats as needed |  |  | 2024-02-06 | 100%
Deliverable: Document data source(s) |  |  | 2024-02-01 | 100% | Captured in presentation slides
Deliverable: Source control project setup
Deliverable: Documentation of work completed and findings
Data Preparation
Codes / Lookup Table |  |  | 2024-02-05 | 100% | Jupyter notebook - DataPrepCodes
Handle missing data |  |  | 2024-02-05 | 100%
Remove duplicate data |  |  | 2024-02-05 | 100%
Verify data integrity and check for outliers |  |  | 2024-02-05 | 100%
Save to Excel |  |  | 2024-02-05 | 100%
Injury Data
Handle missing data |  |  | 2024-02-06 | 100%
Remove duplicate data |  |  | 2024-02-06 | 100%
Look for and cleanup miscoded data
Verify data integrity and check for outliers
Save to CSV
Deliverable: Published dataset ready for EDA
Deliverable: Documentation of work completed and findings
Exploratory Data Analysis
Statistical analysis
Exploratory Data Analysis
Number of injuries
Type and severity of injuries
Patient demograhics
Products involved
Hospital characteristics
Data Visualizations
Deliverable: Checklist of questions to be explored
Deliverable: Documentation of work completed and findings
Validation and QA
Review findings
Validate process
Validate data
Deliverable: Documentation of work completed and findings
Deliverable: Review objectives - is more work needed?
Visualization and Presentation
Review all past deliverables for clarity and consistency
Craft a compling story
Document recommendations
Deliverable: Final visualizations
Deliverable: Final presentation
Project Closeout
Check-in all final code and documentations
Publish project assets and findings as appropriate
Data Collection
NEIS data downloads | 2024-01-19 | 2024-01-19 | 2024-01-19 | 100% | Excel files from 2013 - 2022
Load injury data to Azure SQL | 2024-01-19 | 2024-01-19 | 2024-01-19 | 100% | Database name = ProductInjury
Data Preparation
Validate (and correct) consistency of variables names | 2024-01-19 | 2024-01-19 | 2024-01-19 | 100% | Validated Manually in MSSM
Validate (and correct) consistency of codes / labels | 2024-01-19 | 2024-01-19 | 2024-01-24 | 100% | Python Notebook - DataPrepCodes
Load scrubbed codes and labels to Azure SQL | 2024-01-19 | 2024-01-19 | 2024-01-28 | 100% | Imported using MSSM
Validate and merge injury datasets | 2024-01-28 | 2024-01-28 |  | 50% | Python Notebook - DataPrepInjuries
Load injury data to Azure SQL |  |  |  |  | Python Notebook - DataPrepInjuries
Data Analysis
Number of products tracked
Distribution of injuries by product
Findings / Presentation
Review DataPrepCodes notebook
Project Close Out

## Analysis Checklist
Metric / Report / Graph | Status
# of Product Tracked

## Issue Log
Issue | Issue Type | Date Entered | Date Resolved | Status | Resolution
Cannot read neiss2020, neis2021, or neis2022 Excel files. The folowing error is produced: Unable to read workbook: could not read properties from <filename>. | File Format | 2024-01-18 | 2024-01-19 | Closed | Resolved this issue for each file by copying the data to a new Excel file.
Warninng reading Data Dictionary | File Format | 2024-02-02 | 2024-02-02 | Closed | Cleared print area in Excel and saved file

## Data Cleanup Log
Issue | Issue Type | Date Entered | Status | Resolution
Variable name mismatch - before 2020 Narrative was used, from 2020 on, Narrative_1 is used | Variable Name Consistency | 2024-01-11 | Closed | Updated column names in MSSM using the Design feature
Non-numeric data in Strating and Ending values in code / label data | Data Type Issue | 2024-01-15 | Closed | Stripped spaces and deleted rows with a '.' as a starting or ending value in Python
Product codes with missing labels | Data Issue | 2024-01-19 | Closed | Deleted rows in Python
Age > 200 is under 2 years and translates to age in months using the codes table |  | 2024-01-16 | Open
Age 0 = unknown, not less than 1, 16 occurances of unknown age |  | 2024-01-16 | Open
Codes table contains null rows |  | 2024-01-16 | Open
Labels for Fire codes are unclear and should be updated per page 43 of the manual |  | 2024-01-17 | Open