## Project Plan
Product Injury Data Analysis
Action | Start Date | Target Date | Date Completed | % Complete | Notes
Project Setup
Define goals | 2024-01-19 | 2024-01-19 | 2024-01-19 | 100% | Documented in PowerPoint
Identify data sources | 2024-01-19 | 2024-01-19 | 2024-01-19 | 100% | NEISS data - www.cpsc.gov
Setup source control | 2024-01-19 | 2024-01-19 |  | 50% | GitHub - /tamimcm416/product_injury
Data Collection
NEIS data downloads | 2024-01-19 | 2024-01-19 | 2024-01-19 | 100% | Excel files from 2013 - 2022
Load injury data to Azure SQL | 2024-01-19 | 2024-01-19 | 2024-01-19 | 100% | Database name = ProductInjury
Data Preparation
Validate (and correct) consistency of variables names | 2024-01-19 | 2024-01-19 | 2024-01-19 | 100% | Validated manually by comparing Design Diagrams created in SSMS. Discrepancies reported in Data Cleanup Log
Validate (and correct) consistency of codes / labels | 2024-01-19 | 2024-01-19 | 2024-01-24 | 100% | Merged and validated in Python
Load scrubbed codes and labels to Azure SQL | 2024-01-19 | 2024-01-19
Normalize NEIS data files
Merge datasets
Validate and format data
Validate data types
Check for missing data
Validate date and number formats
Validate categorical data
Check for bad data
Check for data outliers
Data Analysis
Statistical anaysis
Descriptive analysis
Findings / Presentation
Review DataPrepCodes notebook
Project Close Out

## Issue Log
Issue | Issue Type | Date Entered | Date Resolved | Status | Resolution
What is the Stratum variable in the NEISS 2013 dataset? | Data | 2024-01-11 | 2024-01-19 | Closed | Very Large, Large, Medium, Small, Children's
What is the PSU variable in the NEISS 2013 dataset? | Data | 2024-01-11 |  | Open
Cannot read neiss2020, neis2021, or neis2022 Excel files. The folowing error is produced: Unable to read workbook: could not read properties from <filename>. | File Format | 2024-01-18 | 2024-01-19 | Closed | Resolved this issue for each file by copying the data to a new Excel file.

## Data Cleanup Log
Issue | Issue Type | Date Entered | Status | Resolution
Variable name mismatch - before 2020 Narrative was used, from 2020 on, Narrative_1 is used | Variable Name Consistency | 2024-01-11 | Closed | Updated column names in MSSM using the Design feature
Non-numeric data in Strating and Ending values in code / label data | Data Type Issue | 2024-01-15 | Closed | Stripped spaces and deleted rows with a '.' as a starting or ending value in Python
Product codes with missing labels | Data Issue | 2024-01-19 | Closed | Deleted rows in Python
Age > 200 is under 2 years and translates to age in months using the codes table |  | 2024-01-16 | Open
Age 0 = unknown, not less than 1, 16 occurances of unknown age |  | 2024-01-16 | Open
Codes table contains null rows |  | 2024-01-16 | Open
Labels for Fire codes are unclear and should be updated per page 43 of the manual |  | 2024-01-17 | Open